## Sheet1
Univ. of Miami FinTech Boot Camp
Final Project
Assumptions: |  |  |  | The estimate to finish this project would be:
The project goal is to develop a NFT Marketplace |  |  |  | Hours for the implementation to the present state:
where you can list, buy, sell, transfer NFTs. |  |  |  |  | Time: | hours: | 320
You can mint an NFT, but it is assumed that the art is
brought by the user who wants to mint the NFT | [5 empty] | sub-total cost: | 11538.4615
We assume a salary for a blockchain |  |  |  | Time to complete:
| programmer to be: |  | 75000 |  | Complete Functionality |  | 160
| There is a very large range |  |  |  | Enhanced Functionality |  | 192
| of salaries, we are using a |  |  |  | Unit Testing, Hours: |  | 48
| conservative value. |  |  |  | Implement more robustness: |  | 160
|  | hourly Rate: | 36.0577 |  | System Testing: |  | 96
[5 empty] | Improve error handling: |  | 24
We are assuming that the fiscal load | [5 empty] | Total Hours: | 680
per developer to be around 30%. | [5 empty] | sub-total cost: | 24519.2308
This includes insurance, health care
contributions, etc. |  |  | 30% |  |  |  | 36057.6923
[6 empty] | Fiscal load: | 10817.3077
[6 empty] | Total Cost: | 46875